## Week #6
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Feb 13rd, 2016, 06:00PM | Seungho Han, Meeting facilitator | Y | Budget slides, Reading topic related meterials from 'acm' website, Schedule next meeting | on the day | Feb 20th, 2016
Library | Feiyu Chen, Meeting participant | Y | Reading topic related materials from 'acm' website and summarize (1) | on the day | Feb 20th, 2016
| Saurabh Tiwari, Meeting participant | Y | Reading topic related materials from 'acm' website and summarize (1) | on the day | Feb 20th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Reading topic related materials from 'IEEE' website and summarize (1) | on the day | Feb 20th, 2016
| Sangwon Moon, Meeting participant | Y | Reading topic related materials from 'IEEE' website and summarize (1) | on the day | Feb 20th, 2016

## Week #7
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Feb 20th, 2016, 06:00PM | Seungho Han, Meeting facilitator | Y | Reading meterials from 'acm' website (2), Budget slides, Schedule next meeting | on the day | Feb 27th, 2016
Library | Feiyu Chen, Meeting participant | Y | Reading materials from 'acm' website and summarize (2) | on the day | Feb 27th, 2016
| Saurabh Tiwari, Meeting participant | Y | Reading materials from 'acm' website and summarize (2) | on the day | Feb 27th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Reading materials from 'IEEE' website and summarize (2) | on the day | Feb 27th, 2016
| Sangwon Moon, Meeting participant | Y | Reading materials from 'IEEE' website and summarize (2) | on the day | Feb 27th, 2016

## Week #8
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Mar 1st, 2016, 06:20PM | Seungho Han, Meeting facilitator | Y | Compile relevant information with team member, drafting 'Discussion of relevant topics' of term paper. | on the day | Mar 10th, 2016
Library | Feiyu Chen, Meeting participant | Y | Drafting introduction part of term paper. | on the day | Mar 10th, 2016
| Saurabh Tiwari, Meeting participant | Y | Drafting 'Conclusion' part of term paper. | on the day | Mar 10th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Drafting 'Discussion of relevant topics' part of term paper. | on the day | Mar 10th, 2016
| Sangwon Moon, Meeting participant | Y | Drafting 'Discussion of relevant topics' part of term paper. | on the day | Mar 10th, 2016

## Week #9
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Mar 10th, 2016, 05:45PM | Seungho Han, Meeting facilitator | Y | Compile relevant information with team member, drafting 'Discussion of relevant topics' of term paper. (Continued) | on the day | Mar 23rd, 2016
Stuart Building | Feiyu Chen, Meeting participant | Y | Drafting introduction part of term paper. (Continued) | on the day | Mar 23rd, 2016
| Saurabh Tiwari, Meeting participant | Y | Drafting 'Conclusion' part of term paper. (Continued) | on the day | Mar 23rd, 2016
| Subakar Sundarababu Elango, Meeting participant | N | Drafting 'Discussion of relevant topics' part of term paper. (Continued) | on the day | Mar 23rd, 2016
| Sangwon Moon, Meeting participant | N | Drafting 'Discussion of relevant topics' part of term paper. (Continued) | on the day | Mar 23rd, 2016

## Week #10
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Mar 19th, 2016, 03:00PM | Seungho Han, Meeting facilitator | Y | Review any part of paper with team member. | on the day | Mar 27th, 2016
Skype | Feiyu Chen, Meeting participant | Y | Review 'Introduction' part. | on the day | Mar 27th, 2016
| Saurabh Tiwari, Meeting participant | Y | Review 'Conclusion' part. | on the day | Mar 27th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Review 'Discussion' part | on the day | Mar 27th, 2016
| Sangwon Moon, Meeting participant | Y | Review 'Discussion' part. | on the day | Mar 27th, 2016

## Week #11
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Mar 24th, 2016, 06:00PM | Seungho Han, Meeting facilitator | Y | Make draft PPT Slides | on the day | Mar 31th, 2016
Skype | Feiyu Chen, Meeting participant | Y | Check Introduction' part. | on the day | Mar 31th, 2016
| Saurabh Tiwari, Meeting participant | Y | Check Conclusion' part. | on the day | Mar 31th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Check Discussion' part | on the day | Mar 31th, 2016
| Sangwon Moon, Meeting participant | Y | Check Discussion' part. | on the day | Mar 31th, 2016

## Sheet1
Meeting Date/Time | Team Member Name | Attended Meeting | Task Assigned | Start Date | Completion Date | Comments
Mar 30th, 2016, 05:00PM | Seungho Han, Meeting facilitator | Y | Review draft PPT Slides | on the day | Apr 7th, 2016
Skype | Feiyu Chen, Meeting participant | Y | Compile parts | on the day | Apr 7th, 2016
| Saurabh Tiwari, Meeting participant | Y | Compile parts | on the day | Apr 7th, 2016
| Subakar Sundarababu Elango, Meeting participant | Y | Compile parts | on the day | Apr 7th, 2016
| Sangwon Moon, Meeting participant | Y | Compile parts | on the day | Apr 7th, 2016